## Estimated
SPRINT 1 PLANNING
Team Availability
| Name | Available Hours | Estimation Total
| Truong Gia Huy | 80 | 300 | [9 empty] | On Time
| Ngo Van Kha | 75 | [10 empty] | Lately
| Le Van Xuan | 75 | [10 empty] | Early
| Tran Nguyen Thanh Hong | 70 | [10 empty] | Unfinished
Sprint | Component | Task name | Responsible Member | Total | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | 2021-10-02 | 2021-10-03 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10
1 | Initial Sprint 1 | Sprint Planning Meeting | All member | 20 | 0
|  | Create Sprint Backlog for Sprint 1 | All member | 20 | 0
|  | Create Test Plan document for Sprint 1 | All member | 20 | 0
|  | Architecture Design | All member | 20 | 20 | 0
| Design | Design UI for the Login | Hong | 5 | 5 | 5 | 0
|  | Design UI for the Logout | Xuan | 5 | 5 | 5 | 0
|  | Design UI for the Register | Kha | 5 | 5 | 5 | 0
|  | Design database of application users | Huy | 10 | 10 | 10 | 5 | 0
|  | Design Physical Database | Huy | 10 | 10 | 10 | 10 | 5 | 0
|  | Design Test case of “Login” | Hong | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Design Test case of “Register” | Hong | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Design Test case of “Logout” | Hong | 5 | 5 | 5 | 5 | 5 | 5 | 0
| Implementation | Set up front-end develop environment | All member | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0
|  | Set up back-end develop environment | All member | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0
|  | Set up Database | Huy | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 10 | 5 | 0
|  | Code "Login" back-end | Kha | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 5 | 0
|  | Code UI "Login" | Kha | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 5 | 0
|  | Code "Register" back-end | Xuan | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 5 | 0
|  | Code UI "Register" | Xuan | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 5 | 0
|  | Code UI "Logout" | Huy | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 0
|  | Integrate database into the system | Huy | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
| Testing | Test feature “Login” | Hong | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Test feature “Register” | Hong | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 0
|  | Test feature “Logout” | Hong | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
| Fix Bugs | Fix bug for Sprint 1 | All member | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 5 | 5 | 0
|  |  | Total | 315 | 255 | 235 | 215 | 205 | 200 | 185 | 180 | 135 | 130 | 110 | 100 | 70 | 60 | 45 | 40 | 35 | 25 | 15 | 5 | 5 | 0

## Actual
SPRINT 1 PLANNING
Team Availability
| Name | Available Hours | Estimation Total
| Truong Gia Huy | 84.75 | 330 | [11 empty] | On Time
| Ngo Van Kha | 83.75 | [12 empty] | Lately
| Le Van Xuan | 85.75 | [12 empty] | Early
| Tran Nguyen Thanh Hong | 75.75 | [12 empty] | Unfinished
Sprint | Component | Task name | Responsible Member | Total | Actual | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | 2021-10-02 | 2021-10-03 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10
1 | Initial Sprint 1 | Sprint Planning Meeting | All member | 20 | 20 | 0
|  | Create Sprint Backlog for Sprint 1 | All member | 20 | 20 | 0
|  | Create Test Plan document for Sprint 1 | All member | 20 | 20 | 0
|  | Architecture Design | All member | 20 | 20 | 20 | 0
| Design | Design UI for the Login | Hong | 5 | 5 | 5 | 5 | 0
|  | Design UI for the Logout | Xuan | 5 | 4 | 5 | 5 | 0
1
|  | Design UI for the Register | Kha | 5 | 4 | 5 | 5 | 0
1
|  | Design database of application users | Huy | 10 | 10 | 10 | 10 | 5 | 0
|  | Design Physical Database | Huy | 10 | 10 | 10 | 10 | 10 | 5 | 0
|  | Design Test case of “Login” | Hong | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Design Test case of “Register” | Hong | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Design Test case of “Logout” | Hong | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
| Implementation | Set up front-end develop environment | All member | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0
|  | Set up back-end develop environment | All member | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0
|  | Set up database | Huy | 15 | 12 | 15 | 15 | 15 | 15 | 15 | 15 | 10 | 5 | 0
3
|  | Code "Login" back-end | Kha | 20 | 22 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 5 | 0
|  | Code UI "Login" | Kha | 20 | 24 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 5 | 0
4
|  | Code "Register" back-end | Xuan | 20 | 23 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 5 | 0
3
|  | Code UI "Register" | Xuan | 20 | 25 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 5 | 0
5
|  | Code UI "Logout" | Huy | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 0
|  | Integrate database into the system | Huy | 5 | 9 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
4
| Testing | Test feature “Login” | Hong | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Test feature “Register” | Hong | 10 | 12 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 0
2
|  | Test feature “Logout” | Hong | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
| Fix Bugs | Fix bug for Sprint 1 | All member | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 5 | 5 | 0
|  |  | Total | 315 | 330 | 255 | 235 | 217 | 205 | 200 | 185 | 180 | 135 | 133 | 110 | 100 | 74 | 60 | 53 | 40 | 34 | 22 | 15 | 5 | 5 | 0

## Burn-down-Sprint 1
Estimated | Actual | Date
255 | 255 | 2021-09-20
235 | 235 | 2021-09-21
215 | 217 | 2021-09-22
205 | 205 | 2021-09-23
200 | 200 | 2021-09-24
185 | 185 | 2021-09-25
180 | 180 | 2021-09-26
135 | 135 | 2021-09-27
130 | 133 | 2021-09-28
110 | 110 | 2021-09-29
100 | 100 | 2021-09-30
70 | 74 | 2021-10-01
60 | 60 | 2021-10-02
45 | 53 | 2021-10-03
40 | 40 | 2021-10-04
30 | 34 | 2021-10-05
20 | 22 | 2021-10-06
15 | 15 | 2021-10-07
5 | 5 | 2021-10-08
5 | 5 | 2021-10-09
0 | 0 | 2021-10-10